# DataCrowd Lab – Project Development Plan

This plan covers all development phases of the DataCrowd Lab project – from requirements analysis through design, implementation, testing, deployment, and final presentation. The timeline is spread across 10 weeks, assuming roughly 3–4 hours of work per day (about 15–20 hours per week). Tasks are listed with their descriptions, estimated durations (in days) and scheduled week, priority (using MoSCoW categories: Must, Should, Could), status, a comments field, and a category/type. It serves as a progress tracker (checklist) for the project – as each task is completed, you can update its Status (e.g., to “In Progress” or “Done”) and add any notes in the Comments field. All tasks start as Not Started, and non-mandatory tasks are marked as “Should” or “Could” to indicate lower priority.

## Requirements Analysis & Planning

| Task | Description | Estimated Time | Priority | Status | Comments | Category |
| --- | --- | --- | --- | --- | --- | --- |
| Gather & Document Requirements | Collect all functional and non-functional requirements; define user stories and acceptance criteria. | 2 days (Week 1) | Must | Not Started |  | Docs |
| Define Project Scope & Constraints | Outline project boundaries, assumptions, and constraints (identify in-scope and out-of-scope items). | 1 day (Week 1) | Must | Not Started |  | Docs |
| Identify Stakeholders & Use Cases | Identify all stakeholder roles and capture primary use cases or user stories for each. | 1 day (Week 1) | Must | Not Started |  | Docs |
| Prioritize Requirements (MoSCoW) | Prioritize the requirements and features using MoSCoW method (Must, Should, Could). | 0.5 days (Week 1) | Must | Not Started |  | Docs |

## Design & Architecture

| Task | Description | Estimated Time | Priority | Status | Comments | Category |
| --- | --- | --- | --- | --- | --- | --- |
| Define System Architecture | Design the high-level architecture (services, components, interactions) and create architecture diagrams[1]. | 2 days (Week 2) | Must | Not Started |  | Docs |
| Design Database Schema | Design the database schema, defining key entities (User, Project, Task, etc.) and their relationships (ERD). | 1 day (Week 2) | Must | Not Started |  | Docs |
| Plan API Endpoints & Data Models | Specify the API endpoints for all features and outline request/response data models and data flow. | 1 day (Week 2) | Must | Not Started |  | Docs |
| Set Up Dev Environment & Tools | Initialize project repositories (backend & frontend), set up version control, CI pipeline, and the development environment (e.g. Docker Compose for local dev). | 1 day (Week 2) | Must | Not Started |  | Deployment |
| Design UI/UX Wireframes | Create wireframes/mock-ups for key user interfaces (admin dashboard, task list screen, etc.). | 2 days (Week 3) | Must | Not Started |  | Docs |

## Backend Development

| Task | Description | Estimated Time | Priority | Status | Comments | Category |
| --- | --- | --- | --- | --- | --- | --- |
| Set Up Database & ORM | Configure the PostgreSQL database and set up ORM entities/models for core objects (e.g., define User, Project, Task tables in Spring Boot). | 1 day (Week 3) | Must | Not Started |  | Backend |
| Implement User Authentication (Backend) | Implement user registration, login, and role-based access control in the backend (e.g., using Spring Security for Spring Boot). | 2 days (Week 3) | Must | Not Started |  | Backend |
| Implement Project Management API | Develop backend APIs for project creation, editing, and retrieval (allow admins to create projects and view project lists). | 1 day (Week 4) | Must | Not Started |  | Backend |
| Implement Task Management API | Develop backend logic and endpoints for task definition (triggering task generation) and for retrieving tasks for contributors. | 2 days (Week 4) | Must | Not Started |  | Backend |
| Implement Task Submission & Quality Control | Handle contributor submissions: save results, prevent duplicate task pickups, and implement quality control (e.g., consensus/majority voting logic for multiple submissions). | 2 days (Week 5) | Must | Not Started |  | Backend |
| Implement Basic Analytics & Progress Tracking | Implement functionality to compute project progress stats (e.g., % tasks completed, agreement rate) for the admin dashboard[2]. | 1 day (Week 5) | Should | Not Started |  | Backend |
| Integrate Runner Service API | Implement integration in the backend to call the Runner service for background processing (e.g., automatically generate tasks after a dataset is uploaded). | 1 day (Week 5) | Must | Not Started |  | Backend |

## Frontend Development

| Task | Description | Estimated Time | Priority | Status | Comments | Category |
| --- | --- | --- | --- | --- | --- | --- |
| Implement Frontend API Client | Set up the frontend HTTP client to communicate with backend APIs (configure base URL, handle auth headers, error handling). | 0.5 days (Week 4) | Must | Not Started |  | Frontend |
| Implement User Authentication (Frontend) | Create frontend pages for user sign-up/sign-in and integrate with backend auth APIs (include form validation and feedback on errors). | 1.5 days (Week 4) | Must | Not Started |  | Frontend |
| Develop Admin Dashboard UI | Implement the admin dashboard page to list projects and display key stats (e.g., progress percentage, remaining tasks) for each project. | 2 days (Week 5) | Must | Not Started |  | Frontend |
| Develop Project Creation Form (Frontend) | Implement a form UI for admins to create new projects (upload dataset, set task parameters) and connect it to the backend API. | 1 day (Week 5) | Must | Not Started |  | Frontend |
| Develop Task List & Submission UI | Implement the interface for contributors to view available tasks and submit their annotations/results. | 2 days (Week 6) | Must | Not Started |  | Frontend |
| Implement Admin Review/Results Page | Provide a page for admins to review submitted task results and assess quality (e.g., view multiple submissions per task and their agreement). | 1 day (Week 6) | Should | Not Started |  | Frontend |
| UI Testing & Polish | Test the UI for usability issues, fix any UI bugs, and improve styling/responsiveness as needed. | 1 day (Week 7) | Could | Not Started |  | Frontend |

## Microservices (Runner & ML)

| Task | Description | Estimated Time | Priority | Status | Comments | Category |
| --- | --- | --- | --- | --- | --- | --- |
| Develop Runner Service (Go) | Set up the Runner microservice (in Go) to handle background jobs such as task generation and other data processing[1]. | 2 days (Week 6) | Must | Not Started |  | Backend |
| Implement Task Generation Logic (Runner) | In the Runner service, implement logic to parse uploaded datasets and create task entries (either via backend API calls or direct DB access). | 2 days (Week 7) | Must | Not Started |  | Backend |
| Develop ML Service (Python) – Optional | Prototype an ML microservice (e.g., a Flask API) to train a simple model or provide auto-labeling suggestions (for future enhancement)[3]. | 2 days (Week 7–8) | Could | Not Started |  | ML |
| Integrate ML Service (Optional) | If the ML service is implemented, integrate it by allowing the backend or runner to call the ML service’s APIs for suggestions or result validation. | 1 day (Week 8) | Could | Not Started |  | ML |

## Testing & QA

| Task | Description | Estimated Time | Priority | Status | Comments | Category |
| --- | --- | --- | --- | --- | --- | --- |
| Microservices Integration Testing | Test the integration between the main backend and the microservices (Runner and ML) to ensure they communicate and function correctly together. | 1 day (Week 8) | Must | Not Started |  | Testing |
| Write Unit Tests (Backend) | Create unit tests for critical backend components (e.g., task logic, quality control functions) to verify they work as expected. | 2 days (Week 8) | Must | Not Started |  | Testing |
| Write Unit Tests (Frontend) | Develop unit (or component) tests for key frontend components (forms, API calls) to ensure UI functionality is correct. | 1 day (Week 8) | Should | Not Started |  | Testing |
| End-to-End Integration Testing | Conduct end-to-end testing of the system (simulate user workflows from the frontend through the backend and microservices) and fix any issues found. | 1 day (Week 9) | Must | Not Started |  | Testing |
| Performance & Load Testing | Perform basic load testing to ensure the system can handle concurrent users and tasks; optimize performance where necessary. | 1 day (Week 9) | Could | Not Started |  | Testing |
| Bug Fixes and Refinement | Address bugs and issues discovered during testing; refine and polish application functionality and performance before release. | 2 days (Week 9) | Must | Not Started |  | Testing |

## Documentation

| Task | Description | Estimated Time | Priority | Status | Comments | Category |
| --- | --- | --- | --- | --- | --- | --- |
| Update Requirements & Design Docs | Update the requirements and design documentation to reflect the final implemented system and any changes made during development. | 1 day (Week 9) | Must | Not Started |  | Docs |
| Create User Guide/README | Write a user guide or README document explaining how to set up the system and how project admins and contributors can use DataCrowd Lab. | 1 day (Week 10) | Should | Not Started |  | Docs |
| Document API Endpoints | Prepare API documentation listing all endpoints with their purposes and request/response formats for future reference. | 0.5 days (Week 10) | Should | Not Started |  | Docs |
| Prepare Final Report/Thesis | Compile and write the final project report (thesis), including the project background, design, implementation results, and conclusions. | 3 days (Weeks 9–10) | Must | Not Started |  | Docs |

## Deployment

| Task | Description | Estimated Time | Priority | Status | Comments | Category |
| --- | --- | --- | --- | --- | --- | --- |
| Containerize Application Services | Create Dockerfiles and a Docker Compose configuration for all components (Backend, Frontend, Runner, ML, DB) to facilitate deployment[4]. | 1 day (Week 9) | Must | Not Started |  | Deployment |
| Set Up Deployment Environment | Set up the hosting environment (e.g., provision a server or cloud services, and prepare a managed PostgreSQL database instance). | 1 day (Week 10) | Must | Not Started |  | Deployment |
| Implement CI/CD Pipeline | Configure a Continuous Integration/Continuous Deployment pipeline (e.g., with GitHub Actions) for automated build, test, and deployment of the application. | 1 day (Week 10) | Should | Not Started |  | Deployment |
| Deploy to Production & Final Testing | Deploy the application to the production/hosting environment and perform final smoke testing to ensure everything runs correctly. | 1 day (Week 10) | Must | Not Started |  | Deployment |

## Presentation

| Task | Description | Estimated Time | Priority | Status | Comments | Category |
| --- | --- | --- | --- | --- | --- | --- |
| Prepare Presentation Slides | Create a slide deck covering project objectives, architecture, implementation, and results for the final presentation. | 1 day (Week 10) | Must | Not Started |  | Presentation |
| Rehearse Presentation & Demo | Practice the final presentation and demonstration to ensure a smooth delivery and proper timing. | 0.5 days (Week 10) | Must | Not Started |  | Presentation |
| Final Project Presentation | Deliver the final project presentation and live demo to the evaluation committee (project defense). | 0.5 days (Week 10) | Must | Not Started |  | Presentation |

[1] [2] [3] [4] DataCrowd Lab.docx

file://file_000000004a2871f487a86662f84a2fee